## Product Readiness Checklist
Category | Checklist Item | Mandatory (Y/N) | Status | Owner | Remarks
Governance | Gold Master locked and versioned | Y
Governance | Combined Master Instruction uploaded and enforced | Y
Governance | Versioning Policy implemented in system logic | Y
Governance | Release Notes Template mandatory for updates | Y
Governance | Migration Log enforced for controlled re-mapping | Y
Governance | Version Compatibility Matrix enforced at runtime | Y
Data & Logic | TB → Grouping one-to-one enforcement | Y
Data & Logic | Attribute Matrix integrated | Y
Data & Logic | Validation rules auto-executed | Y
Data & Logic | CARO clause applicability engine tested | Y
Data & Logic | Tax bridge logic tested (book → tax → DTA/DTL) | Y
Data & Logic | Cash-flow logic validated (Indirect method) | Y
Outputs | Schedule III Balance Sheet generation verified | Y
Outputs | Schedule III P&L generation verified | Y
Outputs | Notes to Accounts auto-generation verified | Y
Outputs | CARO-2020 draft report generation verified | Y
Outputs | Tax Audit 3CD schedules generation verified | Y
Outputs | Cash Flow Statement generation verified | Y
Audit & Compliance | Audit trail enabled for all overrides | Y
Audit & Compliance | Filed years lock enforced | Y
Audit & Compliance | Preview vs Filing mode clearly separated | Y
Audit & Compliance | Version ID printed in outputs / metadata | Y
Security & Access | Role-based access control implemented | Y
Security & Access | Partner approval required for migrations | Y
Security & Access | Client-wise data isolation verified | Y
Operational Readiness | Pilot firm onboarded | Y
Operational Readiness | Sample TBs tested across industries | Y
Operational Readiness | User training material prepared | N
Operational Readiness | Support & escalation process defined | Y
Legal & Commercial | Disclaimers embedded in UI and outputs | Y
Legal & Commercial | Terms of use reviewed | Y
Legal & Commercial | Pricing & licensing model finalised | Y